ARKA HEALTH, INC.

COMPLIANCE ROADMAP & CERTIFICATION TIMELINE

Program status, external-claims standard, and certification milestones — suitable for investor and customer diligence

ARKA-RDY-004  ·  Version 1.0  ·  Confidential — May be shared under NDA

| Document No. | ARKA-RDY-004 |
| --- | --- |
| Version | 1.0 |
| Effective Date | June 10, 2026 |
| Last Reviewed | June 10, 2026 |
| Document Owner | Arri Kanna, Founder & Chief Executive Officer — Privacy & Security Officer |
| Approved By | Arri Kanna, Founder & Chief Executive Officer |
| Classification | Confidential — May be shared under NDA |
| Review Cycle | Annual, and upon any material change in operations, systems, or law |

This document contains confidential and proprietary information of ARKA Health, Inc. (“ARKA”). It is furnished for informational and compliance purposes, may not be reproduced or disclosed to any third party without the prior written consent of ARKA, and must be returned or destroyed upon request. Nothing in this document constitutes legal advice.

# 1. WHERE ARKA STANDS TODAY

ARKA Health, Inc. is a pre-commercial clinical-software company. As of June 2026: (a) the complete HIPAA privacy and security policy suite (ARKA-GOV/PRIV/SEC series) has been adopted and is in force; (b) the public demonstration environment processes synthetic data only — no PHI (ARKA-DEMO-001); (c) the initial enterprise risk analysis is complete (ARKA-RDY-001) with remediation underway; (d) a BAA template (ARKA-LGL-001) is ready for counsel-reviewed execution with the first design partners; and (e) SOC 2 and HITRUST e1 readiness programs are active (ARKA-RDY-002/003). HIPAA has no government certification; compliance is demonstrated through exactly this documentation, its implementation, and its evidence trail.

# 2. MILESTONE TIMELINE

| Window | Milestone | Owner |
| --- | --- | --- |
| Q3 2026 | Close R-1/R-2/R-3/R-5 remediations; bind cyber-liability insurance; execute audit-firm engagement letter; begin evidence accrual (access reviews, restore tests, monitoring reviews) | Security Officer |
| Q4 2026 | First independent penetration test; SOC 2 Type I examination (Security, Availability, Confidentiality) as of December 2026 | Security Officer / Auditor |
| Q4 2026 – Q2 2027 | SOC 2 Type II observation period (≥ 3 months); first design-partner BAAs executed; production environment with PHI subject to full control set from day one | CEO / Security Officer |
| Q1 2027 | HITRUST MyCSF e1 self-assessment complete; external assessor engaged | Security Officer |
| H1 2027 | SOC 2 Type II report issued; HITRUST e1 validated assessment submitted for certification | Auditor / Assessor |
| Annually thereafter | Type II re-examination; e1 renewal; risk analysis refresh; policy review cycle | Security Officer |

# 3. ALIGNMENT WITH THE 2025 SECURITY RULE RULEMAKING

ARKA has adopted the principal heightened specifications of the December 2024 OCR proposal as its internal baseline now — mandatory MFA, universal encryption, asset inventory and network mapping, six-month vulnerability scanning, annual penetration testing, segmentation, and seventy-two-hour restoration capability (ARKA-SEC-001, § 5; ARKA-SEC-007). The Company therefore expects no material gap upon finalization of the rule, and tracks the rulemaking docket at each quarterly Committee review.

# 4. EXTERNAL CLAIMS STANDARD

To preserve credibility in hospital security review and investor diligence, all ARKA personnel and materials shall observe the following claims discipline:

| Permitted statements (current) | Prohibited until the referenced artifact exists |
| --- | --- |
| “ARKA maintains a HIPAA compliance program aligned to the Privacy, Security, and Breach Notification Rules, with adopted policies and an annual third-party-validated roadmap.” | “ARKA is HIPAA certified.” (No such certification exists; the phrase signals unsophistication to diligence teams.) |
| “SOC 2 Type I/Type II in progress; report available under NDA upon issuance.” | “SOC 2 compliant / SOC 2 certified.” (Prohibited until the auditor’s report is issued; then say “SOC 2 Type [I/II] examined, report available under NDA.”) |
| “HITRUST e1 readiness underway; certification targeted H1 2027.” | “HITRUST certified” or use of the HITRUST seal. (Prohibited until issuance of the validated assessment.) |
| “Demo environment contains synthetic data only — no PHI.” | Any use of real patient data, however de-identified, to imply live clinical deployment. |

# 5. STANDING DILIGENCE PACKAGE

Upon execution of a non-disclosure agreement, ARKA makes available: this roadmap; the policy index and any requested policies; ARKA-RDY-001 (risk assessment); the BAA template; the Data Security Overview one-pager; and, when issued, auditor and assessor reports. Requests: security@getarka.health.

# DOCUMENT CONTROL & REVISION HISTORY

| Version | Date | Author / Reviewer | Description of Change |
| --- | --- | --- | --- |
| 0.9 | May 22, 2026 | A. Kanna (drafting); external review pending | Initial draft circulated for internal review and counsel comment. |
| 1.0 | June 10, 2026 | A. Kanna, Privacy & Security Officer | Adopted as effective policy of ARKA Health, Inc. by written approval of the undersigned officer. |

# ADOPTION AND APPROVAL

The undersigned, being the duly designated Privacy Officer and Security Officer of ARKA Health, Inc., hereby adopts this document as an official policy of the Company, effective as of the Effective Date set forth on the cover page hereof. This document shall be reviewed no less frequently than annually and upon any material change to the Company’s operations, information systems, or applicable law, and may be amended only in accordance with ARKA-GOV-001 (Information Security & Compliance Program Charter).

ARKA HEALTH, INC.

By: _________________________________

Name: Arri Kanna

Title: Founder & Chief Executive Officer; Privacy & Security Officer

Date: June 10, 2026